## Sheet 1
Version 20181214
Saint Luke Confirmandi: PSR Sun 9am (14); PSR Sun 1030am (14); PSR Mon 430pm (26); Saint Luke School (21); other Catholic school (3); and High School (5)
As of Nov 27, 2018, there are 83 Confirmandi. Roadmap updated on Feb 1, 2019
| 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01
Retreat Milestones |  |  | Parent meeting | Parent meeting | Core Team Meeing. Email update to parents. | Core Team Meeing | Core Team Meeing, Email update to parents. | Core Team Meeing. Parent meeting/Email and Retreat volunteer signup. | Core Team Meeing. Email update to parents. | April 6 - Confirmation Retreat | Confirmation Mass Rehearsal and Mass
Faith Experience (FX) | Review volunteer, parent, and student feedback from last year |  | Identified FX team lead | Meet to review ideas for Faith Experience | Discuss the multiple sessions approach | Finalize approach | Finalize sessions and confirm speakers, rooms, and other needs | Prepare material and handouts | Don Bosco Volunteer Training | Deliver the faith experience sessions | Compile video for after Confirmation mass
[5 empty] | Discuss having a guest speaker(s) |  | Finalize parent volunteer needs | Finalize printing needs and supplies |  |  | Analyze feedback and prepare for next year's improvements.
Retreat Support (RS) | Secure Confirmation Retreat date and Flaherty Hall | Secure Saint Luke School Gym |  | Identified RS team lead | Expand Flaherty Hall access for more rehearsals/setup times | Prepare to order Confirmation Retreat t-shirts for Confirmandi | Order YouCat books. | Setup Sign-up Genius for Volunteers and Actors | Order food, flowers, balloons, and other supplies | Deliver and ensure smooth operation of Confirmatin Retreat | Compile video for after Confirmation mass
| Review volunteer, parent, and student feedback from last year |  | Gain parent volunteers to help with Core Team |  | Gain agreement on budget. Get latest student count. | Prepare to order YouCat books for Confirmandi | Arrange for proper layout of Hall and Narthex | Order Confirmandi gifts (wristbands, stickers, phone covers, hoodies, etc) | Secure printer for check-in and print materials for FX, RS, and Play teams | Communicate with Volunteers before the Retreat for final preparation | Analyze feedback and prepare for next year's improvements.
[6 empty] | Prepare to order skit needed items | Finalize parent volunteer needs and setup Sign-Up Genius | Measure the students in the PSR or Saint Luke School class for robes. | Measure the students in the PSR or Saint Luke School class for robes. | Conduct feedback survey of volunteers, parents, and students.
[6 empty] | Reach out to The Restless for music integration | Confirmed integration of The Restless in Confirmation Retreat | Meet with The Restless at Saint Luke Church
[6 empty] | Identify Confirmandi gifts (prizes and rewards) to order | Parent Con Call to go over Volunteer Needs | Communicate with Volunteers | Communicate with Volunteers
Saving Grace Play (Play) | Review volunteer, parent, and student feedback from last year | Prepare parent session | Give parents an update on Confirmation Retreat | Give parents an update on Confirmation Retreat | Update the play to be a sensory-friendly play | Finalize layout of Flaherty Hall (to include sensory-friendly changes) | Finalize volunteer needs | Finalize printing needs and supplies | Setup Final Rehearsals within the 2-weeks before the Retreat. | Deliver the Play | Compile video for after Confirmation mass
| Identified Play team lead | Communicate with 8th grade Catechists | Meet with Sound and Lighting Team | Meet with Confirmandi about the Play | Meet with Confirmandi about the Play. | Meet with Confirmandi about the Play | Meet with Confirmandi about the Play | Meet with Confirmandi about the Play | Meet with Confirmandi about the Play |  | Analyze feedback and prepare for next year's improvements.
|  | Update the script and song list | Update the script and song list | Update the script and song list | Update the script | Initiate the design team products (posters, program guide) | Finalize the script, song list, and song skits | Finalize prop needs | Integrate Flaherty Hall sound/light into stage management
|  |  | Identify props | Identify props |  | Add roles in Act 3 and work out skits for songs | Prepare the Program Guide | Prepare the Program Guide | Prepare for sensory-friendly explanation to audience before the play.
| 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01